## Overview
DESIGNING COHERENCE · BOOK OF RECORD
Initiative Book of Record
The life story of one initiative. Selection parameters, each persona's commitment, every Convergence Point held, change management, the Conductor's running record, operational metrics, decisions, risks, and the timeline. The complete record of one piece of work, in one place.
One file per initiative. Save as: "BoR_[Initiative_Name]_[YYYY-MM-DD].xlsx". Update weekly. Read aloud at every Convergence Point.
INITIATIVE
INITIATIVE NAME | One sentence. What this initiative is.
COMPANY / NEST | Company > Nest holding this initiative
VISIONARY OWNER | The person who brings this to Selection
CONDUCTOR | The person reading across all six personas weekly
STATUS | Selection / Produce / Validation / Live / Killed
SELECTION DATE | When Selection Point was held
SHIPMENT DATE | Committed at Selection — does not move
VALIDATION DATE | Committed at Selection — does not move
KILL THRESHOLD | If by [date], [condition], we retire
SUCCESS THRESHOLD | By [date], we expect [specific outcome]
LAST UPDATED | Date of last meaningful update to this BoR
HOW TO USE THIS WORKBOOK
• Tabs follow the framework: Overview · Personas · Convergence Points · Change Mgmt · Conductor · Operations · Decisions · Risks · Timeline.
• The Personas tab is the heart — six persona sections, each owned by a named person. Update "Where I am now" weekly.
• Convergence Points tab tracks held CPs with Pass / Partial / Fail status. Partials require a due date and responsible person.
• Decisions, Risks, and Timeline are running logs — append, do not edit history.
• Conductor tab is for the person holding coherence — daily reads, weekly meetings, drift signals.
• Read aloud at every Convergence Point. Currency is the discipline — a Book of Record that has stopped being current has stopped being a Book of Record.

## Personas
TAB 2 · PERSONAS
Personas
Each persona maintains a section. Commitment is set once at Selection — it's what they signed up for. Where I am now updates weekly. Changed this week is the cross-impact the Conductor reads. Open questions are what they need from the room. Deliverables link points to where this persona's actual work lives — Jira epic, Linear project, Figma file, Notion page, GitHub PR, wherever.
V | Visionary | Direction — why we're doing this and what success looks like
OWNER
Commitment at Selection |  |  | What this persona signed up to deliver — set at Selection, not edited later
Where I am now |  |  | Updated weekly. Honest read of current state, not aspirational.
Changed this week |  |  | What moved — for the Conductor's daily reads.
Open questions |  |  | What this persona needs from the room or from another persona.
Deliverables link |  |  | Tool name (Jira / Linear / Figma) + URL where this persona's work lives
B | Builder | Architecture & build — how it gets shaped technically
OWNER
Commitment at Selection |  |  | What this persona signed up to deliver — set at Selection, not edited later
Where I am now |  |  | Updated weekly. Honest read of current state, not aspirational.
Changed this week |  |  | What moved — for the Conductor's daily reads.
Open questions |  |  | What this persona needs from the room or from another persona.
Deliverables link |  |  | Tool name (Jira / Linear / Figma) + URL where this persona's work lives
G | Guardian | Risk & reliability — what cannot break, security, compliance
OWNER
Commitment at Selection |  |  | What this persona signed up to deliver — set at Selection, not edited later
Where I am now |  |  | Updated weekly. Honest read of current state, not aspirational.
Changed this week |  |  | What moved — for the Conductor's daily reads.
Open questions |  |  | What this persona needs from the room or from another persona.
Deliverables link |  |  | Tool name (Jira / Linear / Figma) + URL where this persona's work lives
D | Dealmaker | Commercial — pricing, packaging, sales readiness
OWNER
Commitment at Selection |  |  | What this persona signed up to deliver — set at Selection, not edited later
Where I am now |  |  | Updated weekly. Honest read of current state, not aspirational.
Changed this week |  |  | What moved — for the Conductor's daily reads.
Open questions |  |  | What this persona needs from the room or from another persona.
Deliverables link |  |  | Tool name (Jira / Linear / Figma) + URL where this persona's work lives
S | Storyteller | Narrative — the story the company tells about why this exists
OWNER
Commitment at Selection |  |  | What this persona signed up to deliver — set at Selection, not edited later
Where I am now |  |  | Updated weekly. Honest read of current state, not aspirational.
Changed this week |  |  | What moved — for the Conductor's daily reads.
Open questions |  |  | What this persona needs from the room or from another persona.
Deliverables link |  |  | Tool name (Jira / Linear / Figma) + URL where this persona's work lives
A | Advocate | Adoption — onboarding, support, customer success
OWNER
Commitment at Selection |  |  | What this persona signed up to deliver — set at Selection, not edited later
Where I am now |  |  | Updated weekly. Honest read of current state, not aspirational.
Changed this week |  |  | What moved — for the Conductor's daily reads.
Open questions |  |  | What this persona needs from the room or from another persona.
Deliverables link |  |  | Tool name (Jira / Linear / Figma) + URL where this persona's work lives

## Convergence Points
TAB 3 · CONVERGENCE POINTS
Convergence Points
Convergence Points are the moments this initiative is read aloud — Selection (start), Shipment (ready to ship), Validation (kept, killed, or evolved). Below: the log of CPs held, then the master checklists for each CP type.
CP LOG — HELD CONVERGENCE POINTS
DATE | TYPE | OUTCOME | NOTES (WHAT SURFACED, WHAT WAS DECIDED) | PASS / PARTIAL / FAIL SUMMARY
SELECTION POINT — CHECKLIST (COPY PER SELECTION)
# | CRITERION | STATUS | DUE (IF PARTIAL) | RESPONSIBLE (IF PARTIAL) | NOTES
1 | Customer signal is named with specifics — customers, data, or quotes.
2 | Success threshold is measurable and dated.
3 | Kill threshold is written and committed to in the room.
4 | The trade-off — what we are not doing instead — is named explicitly.
5 | All six personas have a named owner present in the room.
6 | The Shipment date and Validation date are both set and on calendars.
7 | Known risks are surfaced — Guardian and Builder typically have the most.
8 | The Conductor explicitly closes: "We are committing. Disagreements after this room are agreed-to disagreements."
SHIPMENT POINT — CHECKLIST
# | CRITERION | STATUS | DUE (IF PARTIAL) | RESPONSIBLE (IF PARTIAL) | NOTES
1 | The Visionary confirms what was promised at Selection is what is shipping.
2 | The Builder confirms technical readiness — known issues are documented and acceptable.
3 | The Guardian confirms risk posture — what could break, mitigation in place.
4 | The Dealmaker confirms commercial readiness — pricing live, terms updated, sales briefed.
5 | The Storyteller confirms narrative — what story does the company tell on launch day?
6 | The Advocate confirms customer-readiness — onboarding flow, support docs, success path.
7 | The Validation date set at Selection is confirmed unchanged.
VALIDATION POINT — CHECKLIST
# | CRITERION | STATUS | DUE (IF PARTIAL) | RESPONSIBLE (IF PARTIAL) | NOTES
1 | The criteria from Selection — including the kill threshold — are surfaced unedited.
2 | Each persona reports what they actually saw — not what they hoped for.
3 | A clear decision is made: keep, kill, or evolve.
4 | If killed: the work to retire is named, dated, and assigned.
5 | If evolved: a new Selection Point is scheduled. Treat it as new.
6 | The decision and reasoning are written into the Book of Record.
7 | The Conductor names what the company learned about its own decision-making.

## Change Mgmt
TAB 4 · CHANGE MANAGEMENT
Change Management
The political surface area of this initiative. What story is being told, to whom, when. What objections have surfaced and what is being done about each. Whose authority is moving.
POLITICAL IMPACT OF THIS INITIATIVE
Whose authority is this initiative moving? Who gains visibility, who loses control, who needs to be brought in early?
COMMUNICATIONS LOG
WHEN | AUDIENCE | MESSAGE | MESSENGER | CHANNEL | STATUS
RESISTANCE LOG
For every objection raised: surface (what they said) vs. what's actually being protected. Mitigations work when they address what's being protected, not the surface.
FROM | SURFACE OBJECTION | WHAT'S PROTECTED | MITIGATION | STATUS

## Conductor
TAB 5 · CONDUCTOR
Conductor
The Conductor's working surface for this initiative. Daily reads are short notes when scanning the BoR — surfacing inconsistencies and cross-impacts. Weekly meetings are the per-initiative slice of the Conductor's weekly Coherence Layer review. Drift signals are recognised drift patterns starting on this initiative.
DAILY READS
DATE | NOTE (CROSS-IMPACT, INCONSISTENCY, WHAT SURFACED)
WEEKLY MEETINGS
DATE | ATTENDED | NOTES (WHAT SURFACED, CONFLICTS, DECISIONS) | FOLLOW-UPS
DRIFT SIGNALS
Recognised drift patterns on this initiative. The 5 Drift Patterns are: CP Erosion, Conductor Capture, Book of Record Fossilisation, Persona Collapse, Coherence Theatre. See the Implementation Guide for the deep read on each.
DATE | PATTERN | OBSERVED | STATUS | CORRECTION

## Operations
TAB 6 · OPERATIONS
Operations
The operational reality of this initiative as it ships and runs. Adoption, escaped bugs, NPS, custom metrics. These numbers feed Validation. The kill threshold from Selection is compared against what ends up here.
TOP-LINE METRICS
ADOPTION |  |  |  | Usage numbers, % of accounts, time-to-first-use, etc.
ESCAPED BUGS |  |  |  | Bugs that hit users post-ship. Severity, count, top hits.
NPS / CUSTOMER SIGNAL |  |  |  | NPS shift, support ticket trends, customer quotes.
CUSTOM METRICS
Anything else this initiative should be tracked on. Use the kill threshold from Selection as the bar.
METRIC NAME | CURRENT VALUE | TARGET | NOTE

## Decisions
TAB 7 · DECISIONS
Decisions
A running record of decisions taken. Where a decision was made matters as much as what — Selection Points carry more weight than hallway calls. Decisions taken outside the framework should still be logged, with the forum named honestly.
DATE | DECISION | BY | FORUM | RATIONALE

## Risks
TAB 8 · RISKS
Risks
Each risk has a named owner — not a team, not "engineering," a person. A risk without an owner is a risk that will be discovered, not addressed. Status: Open · Monitoring · Mitigated · Hardened · Closed.
RISK | OWNER | STATUS | MITIGATION

## Timeline
TAB 9 · TIMELINE
Timeline
Manual timeline notes for this initiative. Customer calls, milestone moments, external events that affect the work. Append, do not edit history.
DATE | NOTE